## Project Schedule
Task Name |  |  | Duration | Start Date | End Date | NOVEMBER |  |  |  |  | J A N U A R Y | [18 empty] | F E B R U A R Y | [19 empty] | M A R C H
[6 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11
[6 empty] | 5 | 6 | 7 | 8 | 9 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15
1. Topic Proposal |  | Plan | 3 days | 2012-11-07 | 2012-11-09 | bar: WEEK 1 7 to WEEK 1 9
|  | Actual | 2 days | 2012-11-08 | 2012-11-09 | bar: WEEK 1 8 to WEEK 1 9
2.Documentation |  | Plan | 3 days | 2012-01-21 | 2012-01-23 | bar: WEEK 4 21 to WEEK 4 23
|  | Actual | 1 day | 2013-01-23 | 2013-01-23 | bar: WEEK 4 23
3. Project Schedule |  | Plan | 1 day | 2013-01-23 | 2013-01-23 | bar: WEEK 4 23
|  | Actual | 2 days | 2013-01-23 | 2013-01-23 | bar: WEEK 4 23
4. Coding for Viewing of Revenues and Expenses |  | Plan | 1 week | 2013-01-28 | 2013-02-01 | bar: WEEK 5 28 to WEEK 5 1
Actual
5. Coding for summary viewing |  | Plan | 1 week | 2013-02-04 | 2013-02-08 | bar: WEEK 6 4 to WEEK 6 8
Actual
6. Booking Schedule (Calendar View, Event List, Add Event) |  | Plan | 3 weeks | 2013-02-11 | 2013-03-08 | bar: WEEK 7 11 to WEEK 10 8
Actual
7. Coding for Viewing of Customers Database |  | Plan | 1 week | 2013-03-11 | 2013-03-15 | bar: WEEK 11 11 to WEEK 11 15
Actual
Legend:
Plan
Actual